## Migration Plan
Step No | Phase | Task | Description | Remarks
1 | Storage Prep | Create LUN | Create new datastore on Hitachi VSP | Match Unity size
2 | Storage Prep | Configure Pool | Select RAID and storage pool | Check performance tier
3 | Storage Prep | Map LUN | Map datastore to Hyper-V hosts | Use correct WWPN
4 | Host | Rescan Disk | Rescan storage on all nodes | Disk should appear
5 | Host | Verify Visibility | Check disk visible on all nodes | Same disk ID
6 | Disk | Bring Online | Set disk online
7 | Disk | Initialize Disk | Initialize as GPT | Required for large disk
8 | Disk | Format Disk | Format with REFS | Best for Hyper-V
9 | Cluster | Add Disk | Add disk to failover cluster
10 | Cluster | Convert to CSV | Convert disk to CSV
11 | Cluster | Rename CSV | Rename CSV properly | Standard naming
12 | Migration | Select VM | Choose VM for migration | Start with low priority
13 | Migration | Move Storage | Use Storage Live Migration | No downtime
14 | Migration | Monitor | Monitor migration progress | Check latency
15 | Validation | Check VM | Verify VM working | No errors
16 | Validation | Verify Path | Ensure new datastore path
17 | Migration | Repeat | Repeat for all VMs
18 | Cleanup | Check Empty | Ensure Unity datastore empty | No files left
19 | Cleanup | Offline Disk | Take disk offline from cluster
20 | Cleanup | Unmap LUN | Unmap from hosts
21 | Cleanup | Delete LUN | Delete after approval